EVENT MANAGEMENT PLAN: MARCH FOR JESUS – BELFAST 2026

1. Event Summary

• Event Title: March for Jesus - Belfast

• Organized by: All Nations Church

• Date: Saturday, 16TH of May

• Locations: Ormeau Park → Belfast City Centre → Donegall Sq. North

• Organizer: All Nations Church - Belfast

• Lead Contact: Gianpaolo Valero

• Phone Number:  +353 87 747 5817

• Email Address: gianpaolo@allnations.ie

• Purpose: March for Jesus Belfast is a large-scale, non-political, family-friendly public event celebrating the Christian faith. The event brings together churches and Christians from across Ireland and Northern Ireland in worship, prayer, and public testimony to exalt the name of Jesus Christ in the heart of Belfast.

• Parades Commission approval:  PAR\106102 - All Nations Church - Belfast - March for Jesus

2. Event Timeline

• Full Event Duration: 8:00 AM – 5:00 PM+ 2 hours for takedown

• March Duration: 2:00 PM – 5:00 PM (start time dependent on PSNI clearance)

• Donegall Sq. North Setup Begins: 8:00 AM

• Event Breakdown Completed By: 7:00 PM

3. Event Locations

• Assembly Point: Ormeau Park – Great Lawn

• Route: Ormeau Park > Ormeau Embankment > Ravenhill Road > Albertbridge Road > East Bridge Street > Cromac Street > Victoria Street > Chichester Street > Arthur Street > Corn Market > High Street > Castle Place > Donegal Place > Donegal Square North > Donegall Sq. North (worship stage, sound system, and crowd reception area)

• Route Length: Approximately 2.8 km / 37-minute walk

• Route coordinated and pre-approved in consultation to Parades Commission

4. Estimated Attendance

• Assembly Area (Ormeau Park): Up to 4,000 participants

• Main Event at Donegall Sq. North: 8,000–12,000 people (final figure subject to confirmation via church engagement and form collection)

5. Programme Schedule

| Time | Activity |
| --- | --- |
| 08:00 AM | Donegall Sq. North stage & AV setup begins |
| 09:00 AM | Organisers and Food Trucks arrive at Ormeau Park |
| 10:00 AM | Public gathering opens |
| 11:00 AM | Volunteer and Marshal briefing (Ormeau Park) |
| 11:30 AM | Safety walkthrough, risk overview, marshal guidelines |
| 01:30 PM | Opening prayer and orientation at Ormeau Park |
| 02:00 PM | March begins (upon PSNI clearance) |
| 02:50 PM | Arrival at Donegall Sq. North; welcome & opening message |
| 03:00 PM | Worship, testimonies, and public prayer |
| 05:00 PM | Event concludes; crowd disperses |
| 07:00 PM | All site breakdowns completed |

6. Key Personnel and Contacts

• Event Coordinator: Gianpaolo Valero +353 87 676 5771 / gianpaolo@allnations.ie

On-the-Day Leads:

- Paul McMichael +44 7769 718418

- Genesis Salumu +353 86 209 9136 / genesis.salumu@allnations.ie

- Naomi Ahern +353 87 942 0399 / naomiahern@allnations.ie

• Health & Safety Officer: TBD- Last year worked with St John’s Ambulance

• Marshals Coordinator: Paul Mc Michael+44 7769 718418

• Stage & AV Coordinator: Jason Clulow +353 87 349 0320

• Stage Supplier: TBC- Last year worked with Castle Hire (Augustine) +353 89 223 8798

• First Aid Lead:  TBD- Last year worked with St John’s Ambulance

7. Safety, Logistics & Traffic Management

• Road Closures & Traffic Control: To be overseen by PSNI

• 200+ Marshals stationed throughout the route with radio comms

• Public barrier system around Donegall Sq. North stage to ensure safe assembly

• Last year: St. John’s Ambulance on-site at both Ormeau Park and Donegall Sq. North; emergency vehicle access maintained throughout-TBC for this year.

• Toilet Provisions:

o Portable toilets at Ormeau Park

o Public toilets requested to be opened along the route and at Donegall Sq. North

o Disabled access and baby-changing included

• Sound Management: Amplified worship and speech systems at Ormeau Park and Donegall Sq. North; coordinated with Council and residents

8. Risk Assessment Summary

Full risk assessment available in Appendix A
Mitigated risks include:

• Crowd movement and congestion

• Trip and slip hazards

• Stage/AV equipment integrity

• Medical emergencies and heat exposure

• Lost children and safeguarding breaches

• Traffic/pedestrian interaction

• Emergency evacuation procedures

9. Emergency Planning

• Emergency Lead: Event Coordinator in contact with PSNI

• Evacuation Routes: Mapped with Council and emergency services

• Lost Children Protocol: Identified points at Ormeau Park & Donegall Sq. North

• Communications: Radios issued to key personnel and marshals; backup via phone network

10. Safeguarding & Inclusion

• Child Protection: Children must be accompanied by guardians

• Safeguarding Policy: Aligned with best practices; copy available upon request

• Accessibility: Wheelchair-friendly route and event areas with clear signage

11. Community Engagement & Compliance

• All speeches vetted to avoid political or provocative content

• Alcohol-free, drug-free, peaceful environment

• Voluntary charity collection buckets at Donegall Sq. North (100% to be donated – Reg. Charity No. 20081768)

• Coordination ongoing with Council, PSNI, DFI, and HSE as required

12. Insurance & Legal

• Public Liability Insurer: TL Dallas

• Policy Number: 104259616

• Coverage Limit: Up to 10,000 attendees

• Entity: UK-based entity formed for compliance post-Brexit

13. Final Coordination meetings

• PSNI and Council: TBD

• Stage/AV Supplier & H&S Officer: Final checks week of event

• Volunteer & Marshal final briefing: Zoom few days before event and in person 1 hour before event

14. Appendices (Separate Documents)

• Appendix A: Full Risk Assessment

• Appendix B: Traffic Management Plan (to be submitted separately)

• Appendix C: Public Liability Certificate (will be attached once confirmed)

• Appendix D: Stewards Operational Guidelines

• Appendix E: Donegall Sq. North Stage & AV Setup Plan

Prepared by

March For Jesus Belfast’s coordination team

March for Jesus – Europe & UK

Date: Latest updates 2nd March 2026