## Sheet1
Existing Precautions to Reduce Risks (HRN)
Activity | Hazards | Existing Precautions | Action by Whom | Action by when | Further Action Required
Public Event | Food Poisoning | No Catering will be offered at City Hall | Gianpaolo Valero- Event Coordinator – All Nations Church | Date? | None
Public Event | Breach of Council Bye-Laws | Speed limits and by- laws relating to public parks and open spaces to be adhered to. | Gianpaolo Valero- Event Coordinator – All Nations Church |  | Advise all attendees accordingly.
Public Event | No risks identified/ No planning/ No liaising | Risk assessment to be completed by experienced assessor. | Gianpaolo Valero- Event Coordinator – All Nations Church |  | None
Public Event | Slips, falls, trips | Cable covers used where required. No trailing wires. Stewards monitor ground conditions. Public liability insurance in place. | Gianpaolo Valero- Event Coordinator – All Nations Church |  | Check weather 24 hours prior
Public Event | Medical emergency | First aid point and emergency response on site. Access routes kept clear for ambulance. | Gianpaolo Valero- Event Coordinator – All Nations Church |  | Brief stewards
Public Event | Overcrowding/crushing | Steward teams allocated to defined zones. Clear routes for pedestrians. | Gianpaolo Valero- Event Coordinator – All Nations Church |  | Radio communication between zone leaders
Public Event |  | Chartered Institute of Environmental Health Level II Award in Principles of Risk Assessment training completed by Assessor. | Gianpaolo Valero- Event Coordinator – All Nations Church